## Weekly GoalsProgress
Week | Goal | Time Log | Progress
0 | Meet w/Winters-Hilt to for solid plan for the semester. | 3.5 hours | Arranged to meet with Winters-Hilt, though due to circumstances, we won't be able to do so until the 1st of Feb. In the meantime, I revised the source code for the data structures that would form the puzzle, greatly streamlining the code and making it more efficient and less memory-intensive. | 1/23-1/29
1 | Modify code to print statements for debugging and finish the auxilary functions for finding roots for the DLS tree | ~5 hours | i. Met w/Winters-Hilt about plan for the project. Decided the main focus will be on DLS tree and on debugging the code for making the puzzle | 1/30-2/5
2 | Debug the methods used to search for sudoku cells that meet specific criteria. Milestone is that the agent should find a cell with the lowest number of possibilities and find one that is a possible value. | 7.5 hours | Restructuring of project to use strategy pattern instead, work on the algorithms is underway, strategies somewhat figured out. | 2/6-2/12
3 | Codework | ~8.5 hours | Abandoned command pattern, implementation of several key classes and algorithms to be used in strategies | 2/13-2/20
4 | Codework | ~12 hours | Implementation of very simple strategies with debugging as part of Agent's functions. All the rough forms of the algorithms for strategies figured out. | 2/20-2/27
5 | Code the Subgroup Exclusion rule and debug the existing search methods | 10 hours | Subgroup exclusion rule coded, fully implemented a strategy class object and came up with idea to use singleton for puzzle. Also implementation of discardedvaluestable | 2/27-3/6
6 | Get the Subgroup Exclusion rule strategy functioning and the baseline for the Hidden Twin strategy written down | 19.5 hours | Full implementation of the strategy pattern with contexts, and the like. Debugging, rewriting the architecture | 3/6-3/12
7 | Finish the second draft of the research paper and get all of the strategies roughly implemented | 9.75 hours | Second draft of paper finished, all the strategies roughly implemented with code entirely refactored | 3/13-3/20
8 | Do work on conditionals, program flow, continued refinement of strategy algorithms | 9 2/3 hours | Contexts and percepts improved upon. Worked on how the program would actuallly flow: begin and end | 3/20-3/26
9 | Finish writing all the contexts and debug the code | ~3.5 hours | Contexts being written and debugged | 3/27-4/2
10 | Get the basic program running and try to fully debug the project within two weeks | 12.75 hours | Got a basic version of the Agent up and running that can solve basic puzzles. Refinements still necessary | 4/3-4/9
11 | Debugging and power point | 39 hours | Massive codework. Flow entirely figured out, solidified, and implemented. Classes finalized, strategy algorithms mostly finalized, powerpoint has prelim work done | 4/10-4/16
12 | Debugging and powerpoint | 7.75 hours | Finished debugging almost all the strategies and contexts and main work was on knowing when puzzle was solved and hidden twin strategy. | 4/17-4/23
13 | Final debugging and presentation preparations | 23 hours | Finished the debugging on all the strategies except the Hidden Twin Strategy (which I decided to simply not implement for this version). Program flow works beautifully. Worked on power points. | 4/24-4/30
14 | Prepare for the presentation, final draft of paper submission | 19.5 hours | Finished the research paper, finalized the program build, finalized the presentation and presented it. | 5/1-5/8

## Sheet1
Date | Time | Duration | Description of activities
2018-01-23 | 10:53 AM - 12:00 PM, 7:23-9:13 PM | 2 hours and 57 minutes | Worked on Clue JSON deserialization, mainly in regards to converting JSON file to a class object
2018-01-26 | 5:13 - 5:43 PM | 30 minutes | Minor work on the depth limited search tree
2018-01-30 | 8:50-10:15 PM | 1 hour and 25 minutes | Made a puzzle JSON file, worked on fill value command, and extensions for Sudoku cell class
2018-02-01 | 12:15-1:30 PM, 2:15-2:30 PM | 1 hour and 30 minutes | i. Met w/Winters-Hilt about plan for the project. Decided the main focus would be on DLS tree and debugging code for making the puzzle
2018-02-03 | 11 AM-12 PM, 7:30-9:15 PM, 9:30 - 10:30 PM | 3 hours and 45 minutes | Created agent class, functions for searching cells and retrieving cells that meet certain criteria w/debugging
2018-02-05 | 7-9 PM | 2 hours | Debugged the deserialization of clue cells
2018-02-06 | 6-8:15 PM | 2 hours and 15 minutes | Debugged the construction of the puzzle fully. The program can now read in a JSON file and convert it into a list of clues succesfully
2018-02-08 | 1:45-2 PM | 15 minutes | Met with Winters-Hilt about the project. Realized that a DLS tree simply won't work very well, thought about programming specific strategies instead
2018-02-10 | 12:30 - 2 PM | 1 hour and 30 minutes | Looked up various Sudoku Puzzle strategies and did some coding work in the agent to implement them.
2018-02-12 | 1:15-4:45 PM | 3 hours and 30 minutes | Wrote CellGroup class, a major data structure meant to represent rows/columns/subgrids, and changed the puzzle class to include collections of them. Purpose is to make it easier for cells to access neighbors or get cells within a specific row/column/subgrid. Work done on Single Possibility strategy and the like
2018-02-13 | 7:30-10 PM | 2 hours and 30 minutes | Implicitly decided to abandon Command Pattern in favor of Strategy pattern, reworked Agent a bit to better fit with CellGroup class
2018-02-14 | 10 AM - 12 PM | 2 hours | Worked on basic algorithms to locate cells and possibilties, attempted to integrate all the new classes
2018-02-18 | 2:06 PM - 5:19 PM | 3 hours and 13 minutes | Began phasing out old structure and figured out the algorithm for finding and filling in cells with just one possiblity.
2018-02-22 | 1:08 PM - 2:48 PM | 1 hour and 40 minutes | Debugged the single possiblity strategy some more
2018-02-24 | 12-1 PM, 5-7:15 PM | 3 hours and 15 minutes | Debugged the function to find all cells with only one possible fill value in the puzzle, wrote another puzzle json file
2018-02-27 | 10:45 AM - 5:52 PM | 7 hours | Wrote crude and basic algorithms for the strategies to be used by the agent, primiarily struggled with dealing how to handle in situations where a cell fill value turns out not to work.
2018-02-28 | 1:15-4:30 PM | 3 hours and 15 minutes | Wrote a collection class used for each row/column/subgrid in puzzle that's used by the search methods. Worked on the Subgroup Exclusion strategy
2018-03-03 | 12-1 PM, 1-4 PM | 4 hours | Finished writing functions for the Subgroup Exclusion strategy.
2018-03-05 | 12:30-3 PM | 2 hours and 30 minutes | Worked on the Hidden Twin strategy, gave serious consideration to turning each strategy into separate classes that reference a singular puzzle and that's contained within agent instead of being a bunch of functions within agent class
2018-03-06 | 1-1:40 PM, 4:15-5 PM, 9:45-11 PM | 3 hours and 40 minutes | Wrote data structures for a FrequencyCounter and Two Key Dictionary. Wrote data structures for a FrequencyCounter and Two Key Dictionary
2018-03-07 | 11:25 AM - 12:30 PM, 3-4:55 PM | 2 hours | Constructed helper classes and implemented the basic strategy pattern, writing the basic strategy class. Wrote rough class for Hidden Twin Strategy
2018-03-09 | 11:40 AM-12:20 PM, 12:50-1:40 PM, 5:15-6:15 PM | 2 hours and 30 minutes | Continued work on the strategy pattern, wrote basic classes for the single possiblity, only choice, subgroup exclusion, and naked twin strats and began decoupling the functions needed from the agent.
2018-03-10 | 11:25 AM - 5 PM, 5-5:50 PM | 6 hours and 25 minutes | Refactored the projcet setup to implement a singleton puzzle pattern and the like. Also rewrote methods/classes to accomodate the pattern. Finished the algorithm for the HiddenTwinStrategy class. Edited the methodology section in research paper
2018-03-11 | 7:45 PM - 8:45 PM, 9:20-10:05 PM | 1 hour and 45 minutes | Continued work on the research paper
2018-03-12 | 11:45 AM - 1:20 PM, 2:30 PM - 3:10 PM, 4:10 PM - 5:15 PM | 3 hours and 20 minutes | Finished the next draft of the resarch paper and implemented the Only Choice Strategy
2018-03-16 | 12-1:30 PM, 3:20-4:43 PM | 2 hours and 53 minutes | Finished writing the Naked Twin Exclusion Strategy, revised classes for SudokuCell, CellGroup, etc. Came up with a base plan for the program flow and basic conditions to check for strategies
2018-03-19 | 4-7:10 PM | 3 hours and 10 minutes | Code refactoring, started adding in conditionals and did revisions for Subgroup Exclusion
2018-03-20 | 3:40-5:10 PM | 1 hour and 30 minutes | Heavily revised and simplified Subgroup Exclusion Strategy
2018-03-21 | 3-3:40 PM, 4:20-5:30 PM, 6:30-7:00 PM | 2 hours and 20 minutes | Added basic contextual conditions for other strategies to the agent.
2018-03-23 | 1:40-2:20 PM, 2:40-3:40 PM, 9:10-9:40 PM | 2 hours and 10 minutes | Cleaned up some code for NakedTwinContext, began adding/brainstorming methods to prevent program from going into infinite loop
2018-03-25 | 1:10-1:50 PM, 9-10 PM | 1 hour and 40 minutes | Did groundwork on converting contexts into class objects with algorithms. Made a Context abstract class and then wrote the OnlyChoiceContext and SinglePossibilityContext classes, and did some work on SubgroupExclusionContext class
2018-03-26 | 3:30-4:26 PM, 9-10:03 PM | 1 hour and 59 minutes | Implemented the algorithms for the Naked and Hidden Twin Contexts as classes, cleaned up some of the Subgroup Exclusion Context a bit
2018-03-27 | 12-1 PM, 1:45-2:10 PM | 1 hour and 25 minutes | Continued refactoring the Context code (mainly for the twin strategies) and met with Winters-Hilt
2018-04-02 | 12:42-2:38 PM | 1 hour and 56 minutes | Refactored the various contexts, strategies, classes to be more runtime efficient.
2018-04-03 | 3-4:20 PM, 6:10-8:10 PM | 3 hours and 20 minutes | Implemented the program flow to make it an actual runnable program. Then began full work on debugging it.
2018-04-06 | 9:20 PM - 11 PM | 1 hour and 40 minutes | Debugging work, figured out and solved a major bug that caused even simple puzzles to be unsolvable.
2018-04-09 | 1:15-4:30 AM, 9:30 AM - 1:50 PM | 7 hours and 45 minutes | Went over program flow and attempted to refine and debug all the algorithms for the contexts and strategies into final version. Settled on final program flow.
2018-04-10 | 8:56 AM - 9:48 AM, 3:55 PM - 8:50 PM, 10:30-11:15 PM | 5 hours and 37 minutes | Primary focus was figuring out the full debugging of the context of rhte HiddenTwinStrategy to operate the algorithm properly. Found Map Reduction to be the perfect parallel and began writing an algorithm to put it in such a context. Also worked on the main image for the presentation that is a visual representation of the process and will serve as the central slide
2018-04-11 | 1:40 PM - 2:53 PM, 5:04 - 6:04 PM | 2 hours and 13 minutes | Continued work on map reduction, debugged and rewrote other strategies as needed, but especially the subgroup exclusion and the twins
2018-04-12 | 10:06 AM-9:17 PM, 10:14 PM - 12:43 AM | 13 hours and 50 minutes | Massive work on debugging everything, focused on getting all the strategies to work and for the puzzle certification to work. Program flow was the main focus. The days really blurred together here. Also did some work on the powerpoint.
2018-04-13 | 3:07 - 3:32 PM, 4:49 - 6:40 PM, 7:55 - 10:49 PM | 5 hours and 10 minutes
2018-04-14 | 12:39 AM - 2:04 AM, 10:16 AM - 2:37 PM, 6:12 PM - 8:47 PM, 9:21 PM - 11:47 PM | ~10 hours
2018-04-15 | 12:37 AM - 2:11 AM, 10:43 AM - 11:50 AM | 2 hours and 40 minutes
2018-04-17 | 9:30 - 10:30 PM, 10:50 PM - 1:46 AM | ~4 hours | Heavy debugging, determined that the main cause of errors in current build was due to the SubgroupExclusion strategy. Decided to make it more efficient and accurate by adding helper functions to various classes to make it easier and rewrote the context for it. Also worked on the powerpoint
2018-04-23 | 12 PM - 1:45 PM, 4-6 PM | 3 hours and 45 minutes | Got the single possibility and only choice strategies/contexts debugged fully and worked on the same for subgroup exclusion.
2018-04-24 | 12 AM - 6 AM, 6 PM - 9:45 PM | 12 hours and 45 minutes | Powerpoint presentation was worked on and got big expansion. Also got all the necessary helper classes debugged, got the most of the strategies debugged except for naked twin? Basically mostly finished coding wise.
2018-04-29 | 1:12 - 1:46 AM, 4:30 - 8:30 PM | 5 hours and 14 minutes | Got all the strategies except the hidden twin strategy fully debugged, decided to give up on that
2018-04-30 | 1 PM - 5:30 PM, 9:24 - 9:54 PM | 5 hours | Powerpoint presentation and paper was the focus, added last touches to agent and program classes
2018-05-01 | 3:25 AM - 5 AM, 9-10 PM | 2 hour and 30 minutes | Focused primarily on the powerpoint presentation, slides for all the major talking points
2018-05-04 | 1-1:41 AM, 3:35-5:35 PM | 2 hours and 40 minutes | Began full rewrite of research paper
2018-05-05 | 12:30 - 2:30 PM, 4:40 - 6 PM, 8:30 - 9:30 PM | 2 hours and 30 minutes | Continued rewriting research paper and practicing final presentation
2018-05-06 | 5:20 PM - 10:30 PM | 5 hours and 10 minutes | Lots of work on the research paper and powerpoint
2018-05-07 | 1:47 - 3:30 AM, 5-5:30 AM, 8-8:25 PM | 2 hours and 13 minutes | Mostly finished the paper and almost completely finished the power point
2018-05-08 | 2:30 - 4:30 PM, 6-8:30 | 4 hours and 30 minutes | Day of presentation, finished paper, code, and everything else.